Gateway Review Process

SRO and PM briefing note

Contents

1.	SRO/PM briefing note	1

1.1	Introduction	1

2.	Role of the SRO in a Gateway Review	2

3.	Role of the PM in a Gateway Review	3

3.1	Responsibilities of the PM in arranging the planning day	3

3.2	Responsibilities of the PM in arranging a Gateway Review	3

4.	Setting up a Gateway Review	4

4.1	Booking a Gateway Review	4

4.2	Project Profile Model	4

4.3	The Assessment Meeting	4

4.4	The Planning Meeting	4

4.5	During the Gateway Review	5

5.	The Gateway Report	6

6.	RAG Status of the project	7

6.1	Red Amber Green (RAG) definition	7

6.2	Individual recommendations (criticality)	7

6.3	Overall Assessment (Delivery Confidence)	8

7.	Confidentiality and disclosure	9

8.	Review Feedback	10

8.1	SRO Feedback Survey	10

9.	Where to find additional information	11

9.1	Gateway website	11

9.2	Gateway helpdesk	11

9.3	Acronyms used in Gateway documentation	11

# SRO/PM briefing note

## Introduction

This note provides the Senior Responsible Owner (SRO) and Project Manager (PM) with key information about their roles and actions required for a successful Gateway Review to be undertaken.

Throughout the note, words highlighted in blue lettering enable you to hyperlink to the Victorian Gateway Review website for additional information and best practice guidance.

# Role of the SRO in a Gateway Review

As the person accountable for the successful outcome of the Project the Gateway Review Team will regard the SRO as the client. The SRO is expected to commission and support the Gateway Review and ensure that all necessary information is made available to the Review Team.

The Review Team Leader (RTL) will present the SRO with a Draft Report at the conclusion of the review. After 7 days to consider any minor edits the final report is provided to the SRO and the Gateway Review is closed. It is expected that the SRO will take ownership of the recommendations in the report and ensure that appropriate actions are taken to address the recommendations in the advised time-scale. For High Value / High Risk (HV/HR) projects any individual ‘red’ recommendations will need to be presented to DTF in the form of a Recommendation Action Plan (RAP) with an indication of actions to be taken to address the identified issues.

It is important to note that the Gateway Review will be severely impacted if the SRO does not make themselves available to participate at key stages of the review e.g. the planning session or the final feedback and draft report presented by the Gateway Review Team at the end of the review process.

# Role of the PM in a Gateway Review

The PM is the person who is responsible for the day-to-day progress of the Project. The PM is expected to be the primary interface between the Gateway Review Team and the Project Team throughout the review as well as with the Gateway Unit. A Gateway Unit team member will assess the Project in consultation with the PM and align the appropriate reviewers to the review based upon that discussion.

The PM also works with the RTL to arrange the Planning Meeting, Gateway Review itself as well as making key documents available before the Planning Meeting as well as before and during the Gateway Review.

## Responsibilities of the PM in arranging the planning day

- Providing some pre-reading to give the Review Team an understanding of the project prior to the planning day;

- Booking a meeting room;

- Providing refreshments (lunch, tea, coffee etc) for the Review Team;

- Providing a presentation (30 mins) on the project at the beginning of the planning day; and

- Setting aside another 30 mins for a general discussion with the Review Team at the end of the planning day.

## Responsibilities of the PM in arranging a Gateway Review

- Prior to the review, scheduling appointments with the people that the Review Team would like to speak with during the review and gathering the requested documentation;

- Booking an appropriately sized meeting room;

- Providing refreshments (lunch, tea, coffee etc) for the Review Team;

- Providing a laptop and attached projector for the Review Team to prepare their report;

- Ensuring that the project team members are available for separate discussions (about an hour) during the first day of the review; and

- Ensuring that the SRO is available for a half hour discussion at the end of each day of the review, as well as a 1 hour discussion at the conclusion of the review for the presentation of the draft report.

# Setting up a Gateway Review

## Booking a Gateway Review

The GRP is mandatory for High Value and/or High Risk (HV/HR) projects. HV/HR projects are defined as:

- all projects with a Total Estimated Investment (TEI) of > $100 million (regardless of funding source);

- projects identified as high risk by application of the Gateway Project Profile Model (PPM); and

- Government may also nominate projects to be part of this process.

## Project Profile Model

The PPM is a risk assessment tool customised to suit the Victorian project landscape and is relatively convenient to complete. The PM completes a PPM as the first step in initiating a Gateway Review (if the project has not already been identified under the HV/HR framework). Completion should take no more than one hour and once finalised this document is emailed to the Departmental contact within the Gateway Unit or via the Gateway Helpdesk. Once the PPM has been reviewed by the appropriate Gateway Unit officer will contact the PM, usually within 2-3 business days to arrange an Assessment Meeting.

(PPM link)

## The Assessment Meeting

There will be an Assessment Meeting between members of the project team and the Departmental Gateway Unit contact where confirmation of readiness for Review and target dates for the Planning Meeting and Gateway Review will be decided. The complexity of the Project will also be discussed in order to select the appropriate Review Team skills. The project team may be liable for costs incurred for postponing or cancelling the Gateway Review after it has been booked and Review Team members engaged.

## The Planning Meeting

The Planning Meeting is an essential part of the Gateway Process for a number of reasons.

- It is often the first time a Review Team and Project Team will have met each other

- It gives an opportunity for the Review Team to familiarise themselves with the Project and decide how best to approach the Gateway Review, as well as identifying all of the stakeholders and answering any concerns of the Project Team

A generic Planning Meeting Agenda is available to enable the PM and the RTL to arrange the sequence of the meeting. The Planning Meeting may be attended by a Gateway representative who will assist the RTL by facilitating the meeting to ensure Gateway Process adherence.

As the person accountable for the Project, the SRO’s presence is required to provide the Review Team with a strategic overview of the environment the Project is operating within and to ensure that any of their own concerns can be raised.

Following the planning day the PM is responsible for the review logistics including scheduling appointments with the stakeholders, gathering the requested documentation and coordination meetings rooms/catering requirements.

## During the Gateway Review

For the report to be an accurate review of the Project the SRO will need to be available at agreed points during the Gateway Review, in addition to any fact-finding interviews, to discuss Emerging Findings. These sessions are intended to enable the Review Team to share their early thoughts on the way the Gateway Review is progressing and offers the SRO and PM the opportunity to correct any misinterpretations or ‘off-track’ thinking and to ensure there are no surprises in the Gateway Review report, which is presented on the final day of the review.

# The Gateway Report

The Review Team will present a draft report to the SRO on the final day of the review with the report to be finalised within one week of the last day of the Review. At the presentation of the report the SRO and PM may correct matters of fact. The Red, Amber, Green (RAG) status is not negotiable.

The report will include:

- a project identification number;

- a conclusion with the RAG status of the overall project;

- a RAG status for the key themes of the review;

- for HV/HR projects, a separate section listing all of the individual red recommendations, which the project team can use to develop their  RAP;

- a summary of findings including related recommendations and their individual RAG status; and

- a note of the interviewees and their roles.

The overall RAG Status is not a 'Stop/Go' sign through to the next phase, nor is it a sign of a 'good' or 'bad' project. It is rather an indication of the urgency and criticality for which remedial action is required on a project to achieve success.

# RAG Status of the project

## Red Amber Green (RAG) definition

There are two levels of RAG Status for a project that must be given, using the colour-coded indicators Red, Amber or Green described below. These include:

- Red (Critical) and Amber (Non Critical) for individual recommendations;

- Red, Amber or Green  Delivery Confidence assessment for the overall project

## Individual recommendations (criticality)

The introduction of the RAP has resulted in a change to how individual recommendations are assessed. In the past individual RAG assessments have taken criticality and urgency into consideration. For example if a project had very little time to address a critical recommendation, the recommendation was classed as red. If there was time to address the critical recommendation, then the recommendations was classed as Amber. This was even though the issue and its criticality was still identical to the red rating.

Individual recommendations are now classified as either Critical (Red) or Non Critical (Amber) as per the diagram below. Green is no longer used for individual recommendations.

Criticality – Individual recommendationsError: Reference source not found

| Non critical recommendation _______________________ The project would benefit from the update of the recommendation | Critical recommendation _______________________ Action required |
| --- | --- |

## Overall Assessment (Delivery Confidence)

An Overall Assessment (Delivery Confidence) is also required for each review based on the definitions below. When determining the Overall Assessment the Review Team should refer to their own judgement/expertise to determine the most suitable Delivery Confidence rating.

Delivery Confidence

| Overall Report: Successful delivery of the project to time, cost and quality appears highly likely. _____________________________ There is no major outstanding issues that at this stage appear to threaten delivery significantly. | Overall Report: Successful delivery appears feasible but significant issues already exist, requiring timely management attention. _____________________________ These issues appear resolvable at this stage and if addressed promptly, should not impact on cost, time or quality. | Overall Report: Successful delivery of the project to cost, time and/or quality does not appear achievable. _____________________________ The project many need re-baselining and/or the overall viability reassessed. |
| --- | --- | --- |

# Confidentiality and disclosure

The Gateway Review Process is a partnership between the SRO and the Review Team to increase the project’s chances of success and as such the report produced by the Review Team is confidential to the SRO. Only two copies of the report are routinely made: one for the SRO and the other for the Gateway Unit to extract generic lessons learned. A Review Team that is open and honest with the Project team is key to the success of the Gateway Review and the same courtesy should be expected in return.

The Review Team is required to dispose of the report and any supporting documents immediately after the final feedback session. The RTL will keep a copy of the draft report, incorporating any changes requested by the SRO and submit the final report no later than 7 days after the final feedback sessions. Once submitted the RTL should then destroy all copies/versions of the report.

# Review feedback

The SRO is required to complete a survey that asks for feedback on various aspects of the Gateway Review. The feedback is an important way of ensuring that Best Practice is maintained and that Gateway can learn from the experiences of its reviews.

## SRO feedback survey

http://www.surveymethods.com/EndUser.aspx?CCE8849EC88E9F99CB

# Where to find additional information

The Gateway website contains an electronic version of the Gateway Review Pack, which includes the overview booklet, workbooks for each Gateway Review and lessons learned brochures. This is the primary source of background information for the Gateway Process. A hyperlink is provided below together with the telephone number and e-mail address of the Gateway helpdesk.

## Gateway website

URL link: Gateway website

## Gateway helpdesk

E-mail: 	gateway.helpdesk@dtf.vic.gov.au

## Acronyms used in Gateway documentation

HV/HR	–	High Value High Risk

PM	–	Project Manager

PPM	–	Project Profile Model

RAG	–	Red, Amber, Green

RAP	–	Recommendation Action Plan

RTL	–	Review Team Leader

RTM	–	Review Team Member

SRO	–	Senior Responsible Owner

www.dtf.vic.gov.au

Green is no longer used for individual recommendations